## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
|  | As a < type of user >, I want < some goal > so that < some reason > |  |  | 3
| User Epic | as a user I want to see if the restrant is open or closed so that I can know where to order food now | 60 |  | 6
|  | I want to see the nearby resterants to know what restrant is nearest to me | 40 |  | 6
|  | I want to see the rating of restrants to know which one is the best | 50 |  | 5
|  | I want to see the the mune and the prices of items to know what to order | 95 |  | 1
|  | I want to track my food so that I know when to expect food to arrive | 60 |  | 7
| Restrant owner | as an owner I want to see th traffic on my page to know how many people have seen my restrant | 40 |  | 5
|  | I want to know when is the traffic on app is at the most so that I prepare my restrant for the traffic | 30 |  | 7
|  | I want to know how to pay for announce or advertise on app so that lots of people can see me | 80 |  | 2
| developer | I want to see the orders in DB so that I can trace any errors | 70 |  | 5
|  | I want to have admin access so that I can undo any wronge action | 100 |  | 1

## Task 03
To Do |  |  | In Progress | Testing | Done
1 | Create home page |  | Y
2 | modify home page
3 | make filters for home page
4 | Create dashboard in home page
5 | add content to home page
6 | Creat profile page |  | Y
7 | Create payment page |  | Y
8 | Create tracking page foe delivery
9 | Create tracking system for orders |  |  | Y
10 | Create owner page
11 | Create dashboard for owner
12 | Create statics page for owner
13 | Create advetisment system
14 | Create payment method for ads
15 | Create page for admins
16 | Create DB |  |  |  | Y
17 | Create admin tools |  |  | Y
18 | Create system for each service |  |  |  | Y
19 | Create integration system between all systems |  | Y
20 | Create middleware
21 | Create servers to handle methods and systems
22 | Create taems for sales and support the product
Sprint timeline | Sum of tasks | PLANNED TASKS | REMAINING TASK
1 | 1 | 19 | 19
2 | 1 | 19 | 19
3 | 6 | 18 | 19
4 | 7 | 18 | 18
5 | 9 | 17 | 18
6 | 9 | 17 | 17
7 | 16 | 16 | 16
8 | 17 | 16 | 9
9 | 17 | 9 | 9
10 | 18 | 9 | 8
11 | 18 | 8 | 8
12 | 19 | 8 | 7
13 | 19 | 7 | 7
14 | 19 | 6 | 6

## Conduct spring planing (hidden)
Sprint goals 5/10
UI/UX
we need to have final apperance on mobile app and portal tested with all the features ready from dev taems
we need to select the final color criteria of the app
we need to be ready for the promotions fields hidden in app
Backend dev team
we need to have a sign up cycle ready and sign in
End user must see his profile with all data
we need to link our payment method with fawry and card of any bank
End user see the main page with all the restrants
Front end team
must make every button on screen function of the backend ready scenarios
we must make sure the inteface in fit to the screen and resizable
DB team
we need to integrate between DB team and backend team
we need to make sure the servers save logs for users orders
we need to store users informations
we need to store restrants informations
testing
we need to test and confirm every finished scenario from dev teams